## Sheet1
User Story | Points | Iteration | Checkout | Notes | Test
User can change color of light | 3 | 0
User can change intensity of light | 1 | 0
User can change angle of light | 1 | 0
User can change direction of light | 2 | 0
Interior of tent accurately represents NUDM 2014 tent | 5
User can start and stop animation of light | 1
User can edit animation speed of light | 2
User can select a light from multiple options | 2
User can change camera angle | 2
User can add lights into groups | 4
User can change color of group | 2
User can change intensity of group | 2
User can change angle of group of lights | 2
User can change direction of group of lights | 2
User can edit animation speed of group of lights | 2
User can start and stop animation of group | 2
User can edit keyframe information about light | 3
User can add keyframe to light animation | 4
User can add hotkey to create custom buttons for more advanced control | 4
User can tell if their browser supports WebGL and will work | 1
User can add Gobo to light | 4
User Interface changes even during animated parameter changes | 4
User can start and stop music | 1
User can select music that is playing | 2